## 480 EDU
Mangold Lift Station and Force Main
BID QUANTITIES
No. | DESCRIPTION | UNIT | QTY. | UNIT COST | TOTAL
LIFT STATION, FORCE MAIN, AND GRAVITY MAIN CONSTRUCTION
1 | 10' Dia.Wetwell (Complete), Wetwell Slabs, and Valve Slab | LS | 1 |  | 0
2 | Pumps and Accessories | EA | 2 |  | 0
3 | 4-inch & 6-inch DI Lift Station Wetwell Discharge Piping, Fittings, Pipe Supports, Valves, Freeze Protection, and Accessories | LS | 1 |  | 0
4 | Wetwell Aeration Equipment (Blower, Aerators, Aerator Piping and Hose, Fittings, and Accessories) | LS | 1 |  | 0
5 | Concrete foundations and slabs (Generator, Control Panel, SCADA Tower, and Light Poles) | LS | 1 |  | 0
6 | 3/4" Water Service (Incl. Connection, Meter, Backflow Preventer, Piping, Spigot/Hose Bib, Fittings, 3/4" Isolation Valve, Freeze Protection, Complete) | LS | 1 |  | 0
7 | Electrical, Instrumentation & Controls (Incl. Generator, SCADA, Lighting, Canopy, etc.) | LS | 1 |  | 0
8 | Security Fencing | LF | 551 |  | 0
9 | 16-ft Double Swing Gate | LS | 1 |  | 0
10 | 2" Asphalt Pavement, 8" Compacted Base | SY | 2172 |  | 0
11 | Reinforced Concrete Driveway Apron | LS | 1 |  | 0
12 | Pedestrian Gate | LS | 1 |  | 0
13 | Lift Station and Force Main Testing & Startup | LS | 1 |  | 0
14 | Trench Protection (Wetwell) | LS | 1 |  | 0
15 | 6-inch HDPE (DR 13.5) DIPS | LF | 1706 |  | 0
16 | 8-inch PVC (SDR 26) Gravity Main (Open Cut, All Depths, Includes Testing) | LF | 243 |  | 0
17 | Onsite/Offsite Manholes | EA | 3 |  | 0
18 | Extra Depth Manhole | VF | 15 |  | 0
19 | Tie 8-inch Gravity Main to Existing Upstream MH | LS | 1 |  | 0
20 | Tie Force Main to Existing Downstream MH | LS | 1 |  | 0
21 | Flowable Fill | CY | 16 |  | 0
22 | Trench Protection (Gravity Main & Force Main) | LF | 1949 |  | 0
23 | Sedimentation and Erosion Control (Lift Station, Gravity Main, and Force Main Installation) | LF | 2500 |  | 0
24 | Revegetation | SY | 1651 |  | 0
SUBTOTAL LIFT STATION, FORCE MAIN AND GRAVITY MAIN CONSTRUCTION |  |  |  |  | 0
| Structural Engineering Subconsultant (SCADA Tower & Tower Foundation Design, if not provided by the SCADA Tower manufacturer) | LS | 1 |  | 0
| Construction Staking | LS | 1 |  | 0
TOTAL LIFT STATION, FORCE MAIN AND GRAVITY MAIN CONSTRUCTION |  |  |  |  | 0