## Questions
Addendum 2
No. | Question | Answer
1 | Will there be a set of plans showing the optional drainage designs? | City code states that storm pipes must have 3' of cover. We are pursuing a variance and the city is asking us to get county approval. The optional section is there in case the county denies the variance request. No revised plans will be provided during the bidding. The flow lines will not change the only change will be from pipe to box at the locations specified in the bid form.
2 | Could you let me know if we can add a Bid line item for the RH-15 Headwall on page C5.2 for storm channel B4-1 ? | Line added to bid form for headwall on B4+1
3 | Do yall have any other variations of the CAD you sent? I’m having a real hard time pulling the linework. | Yes, please see CAD file provided with Addendum 2.
6 | Bid tab shows 236SY of sidewalk, plans show 263SY | Sidewalk quantity in Street Section has been revised.
7 | Storm B5 - Bid tab shows 6” Reinforced concrete Riprap (LF) should it be (SY) of 53SY, plans show 72SY | Riprap quantity in Storm B5 Drainage Section has been revised to 72 SY.
8 | Storm B5 – Bid tab shows install 18” steel casing for 8” Water Main 19 LF, plans in the water section are showing 15LF of 24” casing | Line item for steel casing in Storm B5 Drainage Section has been removed. The 15LF of 24" steel casing is included in the Water Section
9 | Laterals – In the plans sheets the note specifies (laterals shall extend to UE) which differs from the lateral detail showing 1’ past the cleanout. If we go by the note in the plans, bid tab shows 5326LF of laterals, plans show 9672LF of laterals. Please clarify where laterals end. | Please extend laterals to the U.E. Typ. The detail shows that the cleanout can go a maximum of 12" past the Property Line if needed. Although the sybology on the plans for sewer laterals indicate otherwise - construction of laterals will end at the clean out.
10 | Bid tab shows tie into existing 8” stub out & remove cleanout and 8” cap 1, plans show 2. | Tie in quantity revised in the Sewer Section of the bid tab.
11 | Bid tab shows 1 tie into existing manhole, plans show no tie into existing manhole. | Tie into existing MH line item removed in Sewer Section of the bid tab.
12 | Bid tab shows 1 Cap and mark line, plans show 2. | Cap and Mark quantity revised in the Sewer Section of the bid tab.
13 | Is there a conduit plan available? | The GVEC design was provided.
14 | Can we Cast-In-Place the box culverts? | Yes. For C-I-P box culverts use TxDoT details CD-SCC34-21 and CD-SCC-MD-20 and any other TxDot details as appropriate.
15 | Bid tab notes show 19141CY of soils stockpiled from Jaro 2&3 grading and unit 4 will barrow 9100CY. Where will the 9100CY to excavate from stockpile to unit 4 get paid under? | The 19141 CY of soils are stockpiled within a future ROW. The excavation of ROW has been revised to include this amount. Unit 4 is an export site and the spoils are to be hauled to the Navarro site.
16 |  | Note: Clearing and Grubbing for Drainage and ROW has been moved to the Drainage and Streets Sections, respectively.
17 |  | Note: 12" Flex Base and 8" Lime trated Subgrade quantities have been updated in the Street Section of the bid form.